## Test Plan
TEST PLAN – Hospital Management System (Accountant Module)
Project Name: | Hospital Management System – Accountant Module
Version: | v1.0
Prepared By: | QA Team
Date: | 27 June 2026
Testing Standard: | ISTQB Foundation Level
Test Environment: | https://hospitalmanagement.app/accountant
Browser: | Chrome / Firefox / Edge (latest)
Test Account: | accountant@gmail.com accountant123
1. OBJECTIVE
Verify that the Accountant module of the Hospital Management System functions correctly, reliably, and securely according to expected behaviour defined by ISTQB testing principles. This includes functional validation of payment management, invoice management, expense tracking, notifications, and profile management.
2. SCOPE – IN SCOPE
✔ TC-LOGIN : Login / Logout functionality
✔ TC-PAY : Manage Payment – Add Invoice, List Invoice, Create Payment
✔ TC-EXP : Manage Expense – Add Expense, Expense Category
✔ TC-NOTIF : Manage Notification – New Notification, List Events
✔ TC-PROF : Update Profile – Change Name/Email/Phone/Address, Change Password
✔ TC-NAV : Navigation, menu links, breadcrumbs, page titles
✔ TC-UI : UI consistency, layout, responsive design
3. SCOPE – OUT OF SCOPE
✘ Admin, Doctor, Pharmacist, Receptionist, Patient modules
✘ Backend / Database / API internals
✘ Performance & load testing
✘ Security penetration testing (beyond basic checks)
Test Level |  |  | Description
Component Testing |  |  | Validate individual UI components (forms, buttons, tables, modals)
Integration Testing |  |  | Verify interaction between modules (e.g., invoice created → appears in list)
System Testing |  |  | End-to-end scenarios covering full accountant workflows
Acceptance Testing |  |  | UAT checklist against expected system behaviour
5. TEST TYPES
Test Type |  |  | Description
Functional Testing |  |  | Verify all features behave as expected
Negative Testing |  |  | Input invalid/boundary data to confirm error handling
UI / Usability Testing |  |  | Check layout, labels, alignment, colour, typography
Regression Testing |  |  | Re-run after bug fixes to ensure no new defects
Smoke Testing |  |  | Quick sanity check that critical paths are working
Boundary Value Analysis |  |  | Test values at exact boundaries (min, max, min-1, max+1)
6. ENTRY CRITERIA
✔ Test environment is accessible (https://hospitalmanagement.app/accountant)
✔ Demo credentials are valid (accountant@gmail.com / accountant123)
✔ Test cases are reviewed and approved
✔ Test data is prepared
✔ Browser(s) are up to date
7. EXIT CRITERIA
✔ All planned test cases executed
✔ All Critical & High severity defects resolved or deferred with approval
✔ Test case pass rate ≥ 90%
✔ RTM shows 100% requirements coverage
✔ Test summary report signed off
8. TEST DELIVERABLES
📄 Test Plan (this document)
📄 Test Scenarios
📄 Test Cases
📄 Bug Report
📄 RTM (Requirements Traceability Matrix)
9. RISKS & MITIGATIONS
Risk |  | Severity |  | Mitigation
Demo data may be reset |  | Medium |  | Use fresh test data before each run
404 on /manage_profile |  | High |  | Document as known bug; test alternative profile URL
Limited test data (only 2 invoices, 3 expenses) |  | Medium |  | Create additional test data during testing
No requirement doc from client |  | Medium |  | Use industry-standard expected behaviour as baseline
10. ROLES & RESPONSIBILITIES
Role |  |  | Responsibility
QA Team |  |  | Write & execute test cases, report bugs
QA Team |  |  | Review test cases, approve plan, sign off

## Test Scenarios
TEST SCENARIOS – Hospital Management System (Accountant Module)
Scenario ID | Module | Scenario Title | Objective | Test Type | Priority | Expected Outcome
TS-001 | Login | Valid Login | Verify accountant can login with correct credentials | Functional | Critical | Dashboard displayed; success toast shown
TS-002 | Login | Invalid Login – wrong password | Verify system rejects wrong password | Negative | Critical | Error message shown; no access granted
TS-003 | Login | Invalid Login – wrong email | Verify system rejects unregistered email | Negative | Critical | Error message shown
TS-004 | Login | Empty credentials | Verify form validates empty fields | Negative | High | Validation messages shown; login blocked
TS-005 | Login | Logout | Verify accountant can logout successfully | Functional | Critical | Redirected to login page; session ended
TS-006 | Dashboard | Dashboard display | Verify dashboard loads with correct widgets & navigation | UI | High | All menu items visible: Manage Payment, Manage Expense, Manage Notification, Update Profile
TS-007 | Manage Payment | Add Invoice – valid data | Verify invoice is created with all required fields | Functional | Critical | Invoice saved; appears in List Invoice
TS-008 | Manage Payment | Add Invoice – missing required fields | Verify form rejects submission with empty required fields | Negative | High | Validation errors displayed
TS-012 | Manage Payment | List Invoice – display | Verify invoice list shows all invoices with correct columns | Functional | High | Columns: Department, Patient Name, Date Created, Due Date, Status, Actions
TS-013 | Manage Payment | List Invoice – search | Verify search filters invoice list correctly | Functional | Medium | Only matching records shown
TS-014 | Manage Payment | List Invoice – export (Copy/CSV/Excel/PDF/Print) | Verify all export buttons work | Functional | Medium | Data exported in correct format
TS-015 | Manage Payment | Invoice status – Unpaid/Paid | Verify invoice status toggles between Unpaid and Paid | Functional | High | Status updates and reflects in list
TS-016 | Manage Payment | Due Date < Date Created | Verify system rejects due date earlier than creation date | Negative | High | Validation error shown
TS-017 | Manage Expense | Add Expense – valid data | Verify new expense is saved with all fields | Functional | Critical | Expense appears in list
TS-018 | Manage Expense | Add Expense – missing fields | Verify form rejects incomplete submission | Negative | High | Validation errors displayed
TS-019 | Manage Expense | Add Expense – zero/negative amount | Verify system rejects zero or negative expense amount | Negative | High | Validation error for invalid amount
TS-020 | Manage Expense | Expense Category – add new | Verify new category is created and saved | Functional | High | Category appears in list with correct ID & name
TS-021 | Manage Expense | Expense Category – duplicate name | Verify system rejects duplicate category name | Negative | Medium | Error or warning shown
TS-022 | Manage Expense | Expense Category – edit/delete | Verify category can be edited or deleted | Functional | Medium | Category updated/removed from list
TS-023 | Manage Expense | List Expenses – search & export | Verify search and export work on expense list | Functional | Medium | Correct filtering and export
TS-024 | Manage Notification | Add Event – valid data | Verify new event is added with all fields | Functional | High | Event appears in event list
TS-025 | Manage Notification | Add Event – End Date < Start Date | Verify system rejects end date earlier than start date | Negative | High | Validation error shown
TS-026 | Manage Notification | Add Event – missing fields | Verify required fields are enforced | Negative | High | Validation errors displayed
TS-027 | Manage Notification | List Events – display & export | Verify events list shows correct columns and exports work | Functional | Medium | Correct data displayed and exported
TS-028 | Update Profile | Change profile info – valid | Verify profile name, email, phone, address can be updated | Functional | High | Profile updated; confirmation message shown
TS-029 | Update Profile | Change profile – invalid email format | Verify system rejects malformed email | Negative | High | Validation error shown
TS-030 | Update Profile | Change password – matching passwords | Verify password changed with matching new/confirm password | Functional | High | Password changed; success message shown
TS-031 | Update Profile | Change password – mismatched passwords | Verify system rejects mismatched password confirmation | Negative | High | Validation error shown
TS-032 | Update Profile | Change password – empty fields | Verify system enforces non-empty password fields | Negative | Medium | Validation errors displayed

## Test Cases
TestCase# | Test Scenario | Pre-Condition | Test Cases | Test Steps | Test Data | Test Objective | Expected Result | Actual Result (v1) | Pass/Fail
LGN-001 | TS-001 | App is accessible; user is on login page | Valid Login with correct credentials | 1. Navigate to https://hospitalmanagement.app 2. Enter Email: accountant@gmail.com 3. Enter Password: accountant123 4. Click Login | Email: accountant@gmail.com Password: accountant123 | Verify Valid Login with correct credentials | User is redirected to Dashboard; success toast 'Cullen kotze Successfully Logged In' is displayed | User is redirected to Dashboard; success toast 'Cullen kotze Successfully Logged In' is displayed | Pass
LGN-002 | TS-002 | App is accessible; user is on login page | Invalid Login – incorrect password | 1. Navigate to login page 2. Enter Email: accountant@gmail.com 3. Enter Password: wrongpass 4. Click Login | Email: accountant@gmail.com Password: wrongpass | Verify Invalid Login – incorrect password | Error message displayed; user remains on login page; no session created | An error message says “Invalid Login Detail” | Pass
LGN-003 | TS-003 | App is accessible | Invalid Login – unregistered email | 1. Enter Email: unknown@test.com 2. Enter Password: any123 3. Click Login | Email: unknown@test.com Password: any123 | Verify Invalid Login – unregistered email | Error message displayed; access denied | An error message says “Invalid Login Detail” | Pass
LGN-004 | TS-004 | App is accessible | Login with empty email field | 1. Leave Email empty 2. Enter Password: accountant123 3. Click Login | Email: (empty) Password: accountant123 | Verify Login with empty email field | Validation error on Email field; login not submitted | Validation error on Email field; “Please fill out this field” | Pass
LGN-005 | TS-005 | App is accessible | Login with empty password field | 1. Enter Email: accountant@gmail.com 2. Leave Password empty 3. Click Login | Email: accountant@gmail.com Password: (empty) | Verify Login with empty password field | Validation error on Password field; login not submitted | Validation error on Password field; “Please fill out this field” | Pass
LGN-006 | TS-006 | App is accessible | Login with both fields empty | 1. Leave Email and Password empty 2. Click Login | Email: (empty) Password: (empty) | Verify Login with both fields empty | Validation errors on both fields; login not submitted | Validation error on Email field; “Please fill out this field” | Pass
LGN-007 | TS-007 | User is logged in as accountant | Logout from dashboard | 1. Click on user avatar or menu 2. Click Logout | Logged-in session | Verify Logout from dashboard | User redirected to login page; session cleared; accessing /accountant redirects to login | User redirected to login page; session cleared; accessing /accountant redirects to login | Pass
LGN-008 | TS-008 | App is accessible; user is on login page and saved | Valid Login with correct credentials and with remember me option | 1. Navigate to https://hospitalmanagement.app 2. Enter Email: accountant@gmail.com 3. Enter Password: accountant123 4. Select Remember Me 5. Click Login | Email: accountant@gmail.com Password: accountant123 | Verify Valid Login with correct credentials and with remember me option | User is redirected to Dashboard; success toast 'Cullen kotze Successfully Logged In' is displayed and saved | User is redirected to Dashboard; success toast 'Cullen kotze Successfully Logged In' is displayed and saved | Pass
LGN-009 | TS-009 |  | Forgot Password | 1. Navigate to https://hospitalmanagement.app 2. Click Forgot Password 3. Enter your email 4. Click Reset Password | Email: accountant@gmail.com | Verify Forgot Password | System redirects user to create a new password | System redirects to “https://hospitalmanagement.app/login/reset_password” And a message “404 Page Not Found The page you requested was not found.” was shown | Fail
DB-001 | TS-010 | User is logged in | Dashboard navigation menu completeness | 1. Inspect sidebar menu 2. Verify all items: Dashboard, Manage Payment, Manage Expense, Manage Notification, Update Profile, Logout | N/A | Verify Dashboard navigation menu completeness | All 6 menu items visible and correctly labelled | All 6 menu items visible and correctly labelled | Pass
DB-002 | TS-011 | User is logged in | Manage Payment sub-menu items | 1. Hover/click Manage Payment 2. Verify sub-items: Add Invoice, List Invoice | N/A | Verify Manage Payment sub-menu items | Sub-menu shows: Add Invoice, List Invoice | Sub-menu shows: Add Invoice, List Invoice | Pass
DB-003 | TS-012 | User is logged in | Manage Expense sub-menu items | 1. Hover/click Manage Expense 2. Verify sub-items: Expense Category, Add Expense | N/A | Verify Manage Expense sub-menu items | Sub-menu shows: Expense Category, Add Expense | Sub-menu shows: Expense Category, Add Expense | Pass
MP-001 | TS-013 | User is logged in; navigate to Manage Payment > Add Invoice | Add Invoice – all valid fields | 1. Enter Invoice Number: INV-001 2. Enter Invoice Title: Test Invoice 3. Select Department: Hepathology 4. Select Patient 5. Set Date Created: 27/06/2026 6. Set Due Date: 30/06/2026 7. Set VAT: 10 8. Set Discount: 0 9. Add invoice entry 10. Set status: Unpaid Invoice 11. Click Save | Dept: Hepathology VAT: 10% Discount: 0 | Verify Add Invoice – all valid fields | Invoice saved; success message shown; invoice appears in List Invoice | Invoice saved; success message shown; invoice appears in List Invoice | Pass
MP-002 | TS-014 | User on Add Invoice page | Add Invoice – Department not selected | 1. Fill all fields EXCEPT Department 2. Click Save | Department: (not selected) | Verify Add Invoice – Department not selected | Validation error on Department field; invoice not saved | System accepts the invoice | Fail
MP-003 | TS-015 | User on Add Invoice page; Department selected | Add Invoice – Patient not selected | 1. Select Department 2. Leave Patient empty 3. Click Save | Patient: (not selected) | Verify Add Invoice – Patient not selected | Validation error on Patient field; invoice not saved | System accepts the invoice | Fail
MP-006 | TS-016 | User on Add Invoice page | Due Date before Date Created | 1. Set Date Created: 27/06/2026 2. Set Due Date: 25/06/2026 3. Click Save | Date Created: 27/06/2026 Due Date: 25/06/2026 | Verify Due Date before Date Created | Validation error: Due Date must be on or after Date Created | System accepts the invoice | Fail
MP-007 | TS-017 | User on Add Invoice page | Invoice status set to Paid | 1. Fill all required fields 2. Select status: Paid Invoice 3. Click Save | Status: Paid Invoice | Verify Invoice status set to Paid | Invoice saved with Paid status; reflects in List Invoice | Invoice saved with Paid status; reflects in List Invoice | Pass
MP-008 | TS-018 | At least 1 invoice exists; navigate to List Invoice | List Invoice displays existing invoices | 1. Navigate to Manage Payment > List Invoice 2. Observe table | Existing invoices in system | Verify List Invoice displays existing invoices | Table shows: Department, Patient Name, Date Created, Due Date, Status, Actions columns | Table shows: Department, Patient Name, Date Created, Due Date, Status, Actions columns | Pass
MP-009 | TS-019 | List Invoice page loaded with ≥2 invoices | List Invoice – Search filter | 1. Type 'Udemy' in Search box 2. Observe filtered results | Search: 'Udemy' | Verify List Invoice – Search filter | Only invoices matching 'Udemy' are shown | Only invoices matching 'Udemy' are shown | Pass
MP-010 | TS-020 | List Invoice page loaded | List Invoice – Export to CSV | 1. Click CSV button 2. Save file 3. Open in spreadsheet | N/A | Verify List Invoice – Export to CSV | CSV file downloaded; contains all visible invoice data | CSV file downloaded; contains all visible invoice data | Pass
MP-011 | TS-021 | List Invoice page loaded | List Invoice – Export to PDF | 1. Click PDF button | N/A | Verify List Invoice – Export to PDF | PDF generated/downloaded with invoice table data | PDF generated/downloaded with invoice table data | Pass
ME-001 | TS-022 | User logged in; navigate to Manage Expense > Expense Category | Add new Expense Category | 1. Enter Category Name: 'Equipment Purchase' 2. Click Save | Name: Equipment Purchase | Verify Add new Expense Category | New category appears in list with auto-generated ID | New category appears in list with auto-generated ID | Pass
ME-002 | TS-023 | User on Expense Category page | Add Expense Category – empty name | 1. Leave Name field empty 2. Click Save | Name: (empty) | Verify Add Expense Category – empty name | Validation error; category not saved | An error message says “Please fill out this field” | Pass
ME-003 | TS-024 | Category 'Drug Purchase' already exists | Add duplicate Expense Category name | 1. Enter Name: 'Drug Purchase' 2. Click Save | Name: Drug Purchase (duplicate) | Verify Add duplicate Expense Category name | System shows error: Category already exists | System accepts the category | Fail
ME-004 | TS-025 | At least 1 category exists with no expenses linked | Delete Expense Category | 1. Click Delete/Action on a category 2. Confirm deletion | Category: 'Bed Purchase' | Verify Delete Expense Category | Category removed from list | Category removed from list | Pass
ME-005 | TS-026 | User logged in; navigate to Manage Expense > Add Expense | Add Expense – all valid fields | 1. Enter Title: 'Office Supplies' 2. Select Category: Drug Purchase 3. Select Method: Cash 4. Enter Amount: 500 5. Select Date: 27/06/2026 6. Click Save | Amount: 500 Method: Cash | Verify Add Expense – all valid fields | Expense saved; appears in List Expenses with correct data | Expense saved; appears in List Expenses with correct data | Pass
ME-006 | TS-027 | User on Add Expense page | Add Expense – missing Title | 1. Leave Title empty 2. Fill remaining fields 3. Click Save | Title: (empty) | Verify Add Expense – missing Title | Validation error on Title field | An error message says “Please fill out this field” | Pass
ME-007 | TS-028 | User on Add Expense page | Add Expense – zero amount | 1. Enter Amount: 0 2. Fill remaining fields 3. Click Save | Amount: 0 | Verify Add Expense – zero amount | Validation error: Amount must be greater than 0 | System accepts the Amount | Fail
ME-008 | TS-029 | User on Add Expense page | Add Expense – negative amount | 1. Enter Amount: -100 2. Fill remaining fields 3. Click Save | Amount: -100 | Verify Add Expense – negative amount | Validation error: Amount must be positive | System accepts the Amount | Fail
ME-009 | TS-030 | List Expenses loaded; expenses exist | List Expenses – Search by title | 1. Type 'Nurse' in Search box | Search: 'Nurse' | Verify List Expenses – Search by title | Only 'Nurse Uniform Purchase' expense shown | Only 'Nurse Uniform Purchase' expense shown | Pass
MN-001 | TS-031 | User logged in; navigate to Manage Notification > New Notification | Add Event – all valid fields | 1. Enter Title: 'Board Meeting' 2. Set Start Date: 28/06/2026 3. Set End Date: 29/06/2026 4. Enter Location: 'Cairo' 5. Enter Description: 'Quarterly board meeting' 6. Click Save | Title: Board Meeting Location: Cairo | Verify Add Event – all valid fields | Event saved; appears in List Events | Feature is not exist | Fail
MN-002 | TS-032 | User on Add Event page | Add Event – missing Title | 1. Leave Title empty 2. Fill remaining fields 3. Click Save | Title: (empty) | Verify Add Event – missing Title | Validation error on Title field | Feature is not exist | Fail
MN-003 | TS-033 | User on Add Event page | Add Event – End Date before Start Date | 1. Set Start Date: 30/06/2026 2. Set End Date: 28/06/2026 3. Click Save | Start: 30/06/2026 End: 28/06/2026 | Verify Add Event – End Date before Start Date | Validation error: End Date must be on or after Start Date | Feature is not exist | Fail
MN-004 | TS-034 | At least 1 event exists | List Events – verify columns | 1. Navigate to Manage Notification 2. Observe events table | N/A | Verify List Events – verify columns | Table shows: Title, Start Date, End Date, Location, Description | Table shows: Title, Start Date, End Date, Location, Description | Pass
UP-001 | TS-035 | User logged in; navigate to Update Profile | Update Full Name with valid data | 1. Clear Full Name 2. Enter: 'John Doe' 3. Click Change (Profile section) | Full Name: John Doe | Verify Update Full Name with valid data | Profile updated; success message shown; name updated in header | Profile updated; success message says “ Congratulations!!! Data Updated Successfully” | Pass
UP-002 | TS-036 | User on Update Profile page | Update Phone Number | 1. Clear Phone Number 2. Enter: '+201234567890' 3. Click Change | Phone: +201234567890 | Verify Update Phone Number | Phone number saved; success message shown | Profile updated; success message says “ Congratulations!!! Data Updated Successfully” | Pass
UP-003 | TS-037 | User on Update Profile page | Update Profile – invalid email format | 1. Enter Email: 'notanemail' 2. Click Change | Email: notanemail | Verify Update Profile – invalid email format | Validation error: invalid email format | Validation error: invalid email format | Pass
UP-004 | TS-038 | User on Update Profile page | Update Profile – empty Full Name | 1. Clear Full Name 2. Click Change | Full Name: (empty) | Verify Update Profile – empty Full Name | Validation error: Full Name is required | Profile updated; success message says “ Congratulations!!! Data Updated Successfully” | Fail
UP-005 | TS-039 | User on Update Profile page | Change Password – matching passwords | 1. Enter New Password: 'NewPass@123' 2. Enter Confirm Password: 'NewPass@123' 3. Click Change (Password section) | New Pwd: NewPass@123 Confirm: NewPass@123 | Verify Change Password – matching passwords | Password updated; success message; can login with new password | Profile updated; success message says “ Congratulations!!! Data Updated Successfully” | Pass
UP-006 | TS-040 | User on Update Profile page | Change Password – passwords do not match | 1. Enter New Password: 'NewPass@123' 2. Enter Confirm Password: 'DiffPass@456' 3. Click Change | New: NewPass@123 Confirm: DiffPass@456 | Verify Change Password – passwords do not match | Validation error: Passwords do not match | Profile updated; success message says “ Congratulations!!! Data Updated Successfully” | Fail
UP-007 | TS-041 | User on Update Profile page | Change Password – empty fields | 1. Leave New Password empty 2. Leave Confirm Password empty 3. Click Change | New: (empty) Confirm: (empty) | Verify Change Password – empty fields | Validation errors on both password fields | Validation errors on both password fields | Pass
NAV-001 | TS-042 |  | Open profile from sidebar | 1. Hover/click profile photo in sidebar 2. Click on My profile | N/A | Verify Open profile from sidebar | System should open the profile | System navigates to “https://hospitalmanagement.app/accountant/manage_profile” and showing “404 Page Not Found The page you requested was not found.“ | Fail
NAV-002 | TS-043 |  | Open inbox from sidebar | 1. Hover/click profile photo in sidebar 2. Click on Inbox | N/A | Verify Open inbox from sidebar | System should open the Inbox | System not responding | Fail
NAV-003 | TS-044 |  | Open Account Setting from sidebar | 1. Hover/click profile photo in sidebar 2. Click on Account Setting | N/A | Verify Open Account Setting from sidebar | System should open the Account Setting | System not responding | Fail
NAV-004 | TS-045 |  | Logout from sidebar | 1. Hover/click profile photo in sidebar 2. Click on Logout | N/A | Verify Logout from sidebar | System should Logout and navigate to Login page | System Logged out and navigated to Login page | Pass
NAV-005 | TS-046 |  | Logout from Navbar | 1. Click profile photo in Navbar 2. Click on Logout | N/A | Verify Logout from Navbar | System should Logout and navigate to Login page | System Logged out and navigated to Login page | Pass
NAV-006 | TS-047 |  | Open profile from Navbar | 1. Click profile photo in Navbar 2. Click on Edit profile | N/A | Verify Open profile from Navbar | System should open the profile | System navigates to Profile page | Pass
NAV-007 | TS-048 |  | Open Settings from Navbar | 1. Click profile photo in Navbar 2. Click on Settings | N/A | Verify Open Settings from Navbar | System should open Settings | System opens the right sidebar without data | Fail
NAV-008 | TS-049 |  | Change Language from Navbar | 1. Click flag photo in Navbar 2. Click on any language | N/A | Verify Change Language from Navbar | System should Change Language to the selected language | System not Change Language | Fail
NAV-009 | TS-050 |  | Back to dashboard from logo in top left corner | 1. Click on the logo in the top left corner | N/A | Verify Back to dashboard from logo in top left corner | System should navigate to dashboard | System navigates to dashboard | Pass
NAV-010 | TS-051 |  | Expand and collapse the sidebar | 1. Click on the list tag n the top left corner | N/A | Verify Expand and collapse the sidebar | System should expand and collapse the sidebar | System expands and collapses the sidebar | Pass
UI-001 | TS-052 |  | Fields names |  |  | Verify Fields names | All fields should be named correctly | In the login page Password field is named “Passord” | Fail

## Bug Report
Defect # | Status | Raised By | Tested on Version | TestCase Id | Steps to Reproduce | Expected Results | Actual Results | Priority | Severity
BUG-001 | Open | QA Team | V1 | LGN-009 | 1. Navigate to https://hospitalmanagement.app 2. Click 'Forgot Password' 3. Enter email 4. Click Reset Password | System redirects user to create a new password | System redirects to https://hospitalmanagement.app/login/reset_password and shows "404 Page Not Found – The page you requested was not found." | High | Critical
BUG-002 | Open | QA Team | V1 | MP-002 | 1. Navigate to Manage Payment > Add Invoice 2. Fill all fields EXCEPT Department 3. Click Save | Validation error on Department field; invoice not saved | System accepts and saves the invoice without selecting a Department | High | Major
BUG-003 | Open | QA Team | V1 | MP-003 | 1. Navigate to Add Invoice 2. Select Department 3. Leave Patient unselected 4. Click Save | Validation error on Patient field; invoice not saved | System accepts and saves the invoice without selecting a Patient | High | Major
BUG-004 | Open | QA Team | V1 | MP-006 | 1. Navigate to Add Invoice 2. Set Date Created: 27/06/2026 3. Set Due Date: 25/06/2026 4. Click Save | Validation error: Due Date must be on or after Date Created | System accepts and saves the invoice with invalid date range | High | Major
BUG-005 | Open | QA Team | V1 | ME-003 | 1. Navigate to Manage Expense > Expense Category 2. Enter Name: 'Drug Purchase' (already exists) 3. Click Save | System shows error: Category already exists | System accepts and saves the duplicate category without any error | Medium | Minor
BUG-006 | Open | QA Team | V1 | ME-007 | 1. Navigate to Manage Expense > Add Expense 2. Enter Amount: 0 3. Fill remaining fields 4. Click Save | Validation error: Amount must be greater than 0 | System accepts and saves the expense with amount = 0 | High | Major
BUG-007 | Open | QA Team | V1 | ME-008 | 1. Navigate to Manage Expense > Add Expense 2. Enter Amount: -100 3. Fill remaining fields 4. Click Save | Validation error: Amount must be positive | System accepts and saves the expense with negative amount (-100) | High | Major
BUG-008 | Open | QA Team | V1 | MN-001, MN-002, MN-003 | 1. Login as accountant 2. Navigate to Manage Notification 3. Look for Add Event / New Notification option | User can add a new event with Title, Start Date, End Date, Location, Description | Feature does not exist – no option to add events in Manage Notification module | Critical | Critical
BUG-009 | Open | QA Team | V1 | UP-004 | 1. Navigate to Update Profile 2. Clear the Full Name field 3. Click Change | Validation error: Full Name is required | System saves the profile with empty Full Name and shows "Congratulations!!! Data Updated Successfully" | High | Major
BUG-010 | Open | QA Team | V1 | UP-006 | 1. Navigate to Update Profile 2. Enter New Password: 'NewPass@123' 3. Enter Confirm Password: 'DiffPass@456' 4. Click Change | Validation error: Passwords do not match | System saves the new password without validating the match and shows "Congratulations!!! Data Updated Successfully" | Critical | Critical
BUG-011 | Open | QA Team | V1 | NAV-001 | 1. Login as accountant 2. Click profile photo in sidebar 3. Click 'My Profile' | System opens the user profile page | System navigates to https://hospitalmanagement.app/accountant/manage_profile and shows "404 Page Not Found" | High | Critical
BUG-012 | Open | QA Team | V1 | NAV-002 | 1. Login as accountant 2. Click profile photo in sidebar 3. Click 'Inbox' | System opens the Inbox page | System does not respond; no navigation occurs; no error message shown | High | Major
BUG-013 | Open | QA Team | V1 | NAV-003 | 1. Login as accountant 2. Click profile photo in sidebar 3. Click 'Account Setting' | System opens the Account Settings page | System does not respond; no navigation occurs; no error message shown | High | Major
BUG-014 | Open | QA Team | V1 | NAV-007 | 1. Login as accountant 2. Click profile photo in Navbar 3. Click 'Settings' | System opens Settings with relevant settings options | System opens the right sidebar panel but it is completely empty with no data or options | Medium | Minor
BUG-015 | Open | QA Team | V1 | NAV-008 | 1. Login as accountant 2. Click flag icon in Navbar 3. Click on any available language | System changes the UI language to the selected language | System does not change the language; UI remains in the original language | Medium | Minor
BUG-016 | Open | QA Team | V1 | UI-001 | 1. Navigate to https://hospitalmanagement.app 2. Observe the label of the password field | Password field is labelled "Password" | Password field is labelled "Passord" – missing the letter "w" | Low | Minor

## RTM
REQUIREMENTS TRACEABILITY MATRIX (RTM) – Hospital Management System (Accountant Module)
Req ID | Requirement Description | Module | Test Scenario ID | Test Case ID(s) | Bug ID(s) | Priority | Coverage | Status
REQ-001 | System shall allow accountant to login with valid credentials | Login | TS-001 | LGN-001 | – | Critical | 100% | Covered
REQ-002 | System shall reject invalid login credentials | Login | TS-002, TS-003 | LGN-002, LGN-003 | – | Critical | 100% | Covered
REQ-003 | System shall validate empty login fields | Login | TS-004 | LGN-004, LGN-005, LGN-006 | – | High | 100% | Covered
REQ-004 | System shall allow accountant to logout | Login | TS-005 | LGN-007 | – | Critical | 100% | Covered
REQ-005 | Dashboard shall display all navigation menu items | Dashboard | TS-006 | DB-001, DB-002, DB-003 | – | High | 100% | Covered
REQ-006 | Accountant shall be able to create an invoice with all required fields | Manage Payment | TS-007 | MP-001 | – | Critical | 100% | Covered
REQ-007 | System shall validate required fields in Add Invoice form | Manage Payment | TS-008 | MP-002, MP-003 | BUG-002, BUG-003 | High | 100% | Covered
REQ-010 | System shall reject Due Date earlier than Date Created | Manage Payment | TS-016 | MP-006 | BUG-004 | High | 100% | Covered
REQ-011 | Invoice shall support Paid and Unpaid statuses | Manage Payment | TS-015 | MP-007 | – | High | 100% | Covered
REQ-012 | List Invoice shall display all invoices with correct columns | Manage Payment | TS-012 | MP-008 | – | High | 100% | Covered
REQ-013 | List Invoice search shall filter results correctly | Manage Payment | TS-013 | MP-009 | – | Medium | 100% | Covered
REQ-014 | List Invoice shall support export (Copy/CSV/Excel/PDF/Print) | Manage Payment | TS-014 | MP-010, MP-011 | – | Medium | 100% | Covered
REQ-015 | Accountant shall be able to add Expense Category | Manage Expense | TS-020 | ME-001, ME-002 | – | High | 100% | Covered
REQ-016 | System shall validate empty Expense Category name | Manage Expense | TS-020 | ME-001, ME-002 | – | High | 100% | Covered
REQ-017 | System shall reject duplicate Expense Category names | Manage Expense | TS-021 | ME-003 | BUG-005 | Medium | 100% | Covered
REQ-018 | Accountant shall be able to delete Expense Category | Manage Expense | TS-022 | ME-004 | – | Medium | 100% | Covered
REQ-019 | Accountant shall be able to add an Expense with all required fields | Manage Expense | TS-017 | ME-005 | – | Critical | 100% | Covered
REQ-020 | System shall validate required Expense fields | Manage Expense | TS-018 | ME-006 | – | High | 100% | Covered
REQ-021 | System shall reject zero or negative Expense amount | Manage Expense | TS-019 | ME-007, ME-008 | BUG-006, BUG-007 | High | 100% | Covered
REQ-022 | Expense list search shall filter correctly | Manage Expense | TS-023 | ME-009 | – | Medium | 100% | Covered
REQ-023 | Accountant shall be able to add a Notification/Event | Manage Notification | TS-024 | MN-001 | BUG-008 | High | 100% | Covered
REQ-024 | System shall validate required Event fields | Manage Notification | TS-026 | MN-002 | BUG-008 | High | 100% | Covered
REQ-025 | System shall reject End Date before Start Date in Event | Manage Notification | TS-025 | MN-003 | BUG-008 | High | 100% | Covered
REQ-026 | Event list shall display correct columns | Manage Notification | TS-027 | MN-004 | – | Medium | 100% | Covered
REQ-027 | Accountant shall be able to update profile information | Update Profile | TS-028 | UP-001, UP-002, UP-004 | BUG-009 | High | 100% | Covered
REQ-028 | System shall validate email format in Update Profile | Update Profile | TS-029 | UP-003 | – | High | 100% | Covered
REQ-029 | System shall validate required profile fields | Update Profile | TS-028 | UP-001, UP-002, UP-004 | BUG-009 | Medium | 100% | Covered
REQ-030 | Accountant shall be able to change password | Update Profile | TS-030 | UP-005 | – | High | 100% | Covered
REQ-031 | System shall reject mismatched password confirmation | Update Profile | TS-031 | UP-006 | BUG-010 | High | 100% | Covered
REQ-032 | System shall validate empty password fields | Update Profile | TS-032 | UP-007 | – | Medium | 100% | Covered

## API Test Cases
Test Case ID | API Name | Method | Expected Result | Actual Result | Status
API_TC_001 | Get Brands | GET | Response Code = 200 and Brands List Returned | Response Code = 200 and Brands Returned | Pass
API_TC_002 | Get Products | GET | Response Code = 200 and Products List Returned | Response Code = 200 and Products Returned | Pass
API_TC_003 | Search Product | POST | Response Code = 200 and Matching Products Returned | Response Code = 200 and Matching Products Returned | Pass
API_TC_004 | Login | POST | Response Code = 200 and User exists | Response Code = 200 and User exists | Pass
API_TC_005 | Register | POST | Response Code = 201 and User created successfully | Response Code = 201 and User created successfully | Pass
API_TC_006 | Update User | PUT | Response Code = 200 and Account updated successfully | Response Body: responseCode = 404, message = "Account not found!" | Fail
API_TC_007 | Delete User | DELETE | Response Code = 200 and Account deleted successfully | Response Code = 200, message = "Account deleted!" | Pass